## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-001 | As a Salesforce Administrator, I want to add the Equifax OneScore (SCR2038) as a new Data Provider Product in BusinessConnect so that credit analysts can access OneScore data for credit decisioning. | This story covers the configuration of the new Equifax OneScore product (SCR2038) in BusinessConnect Data Provider Products. This must be completed before any development work begins as it is a prerequisite for all subsequent stories. Reference: Western EF - 2026 OneScore Change document. Assumption: Equifax will provide the product code and configuration details. | Configuration | • Given the BusinessConnect Data Provider Products configuration page is accessible, When the administrator adds Equifax OneScore with product code SCR2038, Then the product should be successfully created and available for selection in credit workflows. • Given the OneScore product is configured, When a credit report is requested, Then the system should be able to call the OneScore product from Equifax.
US-002 | As a Salesforce Administrator, I want to remove the Equifax Commercial Insight Delinquency Score (CIDS) (SCR0117) from Data Provider Products so that it is no longer available for credit decisioning. | This story covers the removal/deactivation of the legacy CIDS score (SCR0117) from BusinessConnect. This should be done after OneScore is fully configured and tested. Reference: Western EF - 2026 OneScore Change document. Dependency: US-001 must be completed first. | Configuration | • Given the CIDS product (SCR0117) exists in Data Provider Products, When the administrator deactivates or removes the CIDS product, Then the product should no longer be available for selection in credit workflows. • Given CIDS is removed, When users access credit decisioning pages, Then CIDS should not appear as an available score option.
US-003 | As a Salesforce Administrator, I want to add custom fields for PG Fraud Alert and PG Active Duty Alert in BusinessConnect so that these alerts can be captured and displayed in pre-scoring rules. | This story covers the creation of two new custom fields: PG Fraud Alert and PG Active Duty Alert. These fields are required for the new pre-scoring rules (Rules 4 and 5). These fields must be added to Viewed Variables section. Reference: Western EF - 2026 OneScore Change document. Dependency: Must be completed before US-006. | Configuration | • Given the BusinessConnect custom fields configuration is accessible, When the administrator creates PG Fraud Alert and PG Active Duty Alert fields, Then both fields should be successfully created with appropriate data types. • Given the new fields are created, When the fields are added to Viewed Variables, Then they should be visible and accessible in the pre-scoring rules configuration.
US-004 | As a Credit Analyst, I want OneScore to be displayed on the Opportunity page so that I can view the credit score during the opportunity evaluation process. | This story covers adding the OneScore field to the Opportunity page layout in Salesforce, similar to how CIDS was previously displayed. Reference: Slide 6 of BRD. Dependency: US-001 must be completed. Assumption: The field placement and formatting should match the existing CIDS display pattern. | Development | • Given an Opportunity record exists with a completed credit report, When the credit analyst views the Opportunity page, Then the OneScore should be displayed in the appropriate section. • Given the OneScore is displayed, When the score value is present, Then it should be formatted consistently with other credit scores on the page.
US-005 | As a Credit Analyst, I want OneScore to be displayed on the Account page in the Relationship section so that I can view the credit score when reviewing customer accounts. | This story covers adding the OneScore field to the Account page layout in the Relationship section, similar to how CIDS was previously displayed. Reference: Slide 6 of BRD. Dependency: US-001 must be completed. | Development | • Given an Account record exists with a completed credit report, When the credit analyst views the Account page Relationship section, Then the OneScore should be displayed. • Given the OneScore is displayed in the Relationship section, When the score is updated, Then the new value should reflect immediately upon page refresh.
US-006 | As a Credit Analyst, I want OneScore to be displayed on the Equifax Commercial Report page in the Credit Information section so that I can view the score alongside other credit data. | This story covers adding the OneScore field to the Equifax Commercial Report page in the Credit Information section. Reference: Slide 6 of BRD. Dependency: US-001 must be completed. | Development | • Given an Equifax Commercial Report is generated, When the credit analyst views the report Credit Information section, Then the OneScore should be displayed. • Given the OneScore is displayed in the Credit Information section, When the report contains OneScore data, Then the score should be clearly labeled and formatted.
US-007 | As a Credit Analyst, I want OneScore to be displayed on the Decision page in the Scorecard section so that I can view the score during credit decision workflows. | This story covers adding the OneScore field to the Decision page in the Scorecard section. Reference: Slide 6 of BRD. Dependency: US-001 must be completed. | Development | • Given a Decision record exists with a completed credit report, When the credit analyst views the Decision page Scorecard section, Then the OneScore should be displayed. • Given the OneScore is displayed in the Scorecard section, When a credit decision is being made, Then the OneScore should be available for review alongside other decision factors.
US-008 | As a Credit Manager, I want to replace the existing commercial scorecard with a new scorecard that uses OneScore as the primary component for risk rating assignment so that credit decisions are based on the new scoring model. | This story covers the creation and configuration of a new commercial scorecard in BusinessConnect with OneScore as the main scoring component. The scorecard will be used for Primary Decision (Score Decision/Cutoffs) and Risk Rating Assignment. Reference: Slide 7 of BRD. Dependency: US-001, US-004, US-005, US-006, US-007 must be completed. Assumption: Western EF will provide the cutoff values and risk rating mappings. | Development | • Given the new scorecard is configured in BusinessConnect, When a credit report is processed, Then the system should use OneScore as the primary component for scoring. • Given the scorecard is active, When a score decision is made, Then the Risk Rating should be assigned based on the OneScore cutoffs defined in the scorecard configuration. • Given the new scorecard is in use, When the Primary Decision is triggered, Then the system should apply the correct Score Decision based on OneScore thresholds.
US-009 | As a Credit System, I want to add a new pre-scoring rule (Rule 4) for PG Fraud Alert so that applications with personal guarantee fraud alerts are flagged before scoring. | This story covers the implementation of a new pre-scoring rule (Rule 4) to detect and flag PG Fraud Alerts as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-003 must be completed. Clarification needed: What is the specific business logic for the PG Fraud Alert rule? What action should be taken when a fraud alert is detected? | Development | • Given a credit application is being processed, When the pre-scoring rules are executed and a PG Fraud Alert is detected, Then the system should flag the application according to the rule definition. • Given the PG Fraud Alert rule is active, When the rule is triggered, Then the PG Fraud Alert field should be populated in Viewed Variables.
US-010 | As a Credit System, I want to add a new pre-scoring rule (Rule 5) for PG Active Duty Alert so that applications with personal guarantee active duty alerts are flagged before scoring. | This story covers the implementation of a new pre-scoring rule (Rule 5) to detect and flag PG Active Duty Alerts as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-003 must be completed. Clarification needed: What is the specific business logic for the PG Active Duty Alert rule? What action should be taken when an active duty alert is detected? | Development | • Given a credit application is being processed, When the pre-scoring rules are executed and a PG Active Duty Alert is detected, Then the system should flag the application according to the rule definition. • Given the PG Active Duty Alert rule is active, When the rule is triggered, Then the PG Active Duty Alert field should be populated in Viewed Variables.
US-011 | As a Credit System, I want to modify the existing post-scoring rule (Rule 11) for Exceeds App-Only Limit so that it works with the new OneScore model. | This story covers the modification of the existing Exceeds App-Only Limit rule (Rule 11) to align with the OneScore implementation as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-008 must be completed. Clarification needed: What specific changes are required to the Exceeds App-Only Limit rule logic? | Development | • Given a credit application is scored with OneScore, When the post-scoring rules are executed and the application exceeds the app-only limit, Then the system should apply the modified Rule 11 logic. • Given Rule 11 is modified, When the rule is triggered, Then the appropriate decision outcome should be recorded based on the updated rule definition.
US-012 | As a Credit System, I want to add a new post-scoring rule (Rule 22) for Exceeds Comparable Credit so that applications exceeding comparable credit thresholds are handled appropriately. | This story covers the implementation of a new post-scoring rule (Rule 22) for Exceeds Comparable Credit as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-008 must be completed. Clarification needed: What is the definition of 'comparable credit' and what are the threshold values? | Development | • Given a credit application is scored with OneScore, When the post-scoring rules are executed and the application exceeds comparable credit thresholds, Then the system should apply Rule 22 logic. • Given Rule 22 is active, When the rule is triggered, Then the system should record the appropriate decision outcome based on the rule definition.
US-013 | As a Credit System, I want to add a new post-scoring rule (Rule 23) for OneScore Consumer Only so that consumer-only OneScore scenarios are handled according to business rules. | This story covers the implementation of a new post-scoring rule (Rule 23) for OneScore Consumer Only as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-008 must be completed. Clarification needed: What constitutes a 'consumer only' OneScore scenario and what action should be taken? | Development | • Given a credit application is scored with OneScore, When the post-scoring rules are executed and the score is consumer-only, Then the system should apply Rule 23 logic. • Given Rule 23 is active, When the rule is triggered, Then the system should record the appropriate decision outcome based on the rule definition.
US-014 | As a Credit System, I want to remove the existing post-scoring rule (Rule 17) for Low CIDS so that it no longer affects credit decisions after CIDS is removed. | This story covers the removal or deactivation of the Low CIDS rule (Rule 17) as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-002 must be completed. | Development | • Given the CIDS score has been removed from the system, When post-scoring rules are executed, Then Rule 17 (Low CIDS) should not be triggered or evaluated. • Given Rule 17 is removed, When credit decisions are processed, Then the system should not reference or apply Low CIDS logic.
US-015 | As a Credit System, I want to remove the existing post-scoring rule (Rule 19) for No Commercial Data so that it no longer affects credit decisions after migrating to OneScore. | This story covers the removal or deactivation of the No Commercial Data rule (Rule 19) as specified in the Western EF - 2026 OneScore Change document. Reference: Slide 8 of BRD. Dependency: US-008 must be completed. Clarification needed: Should this rule be completely removed or replaced with a OneScore-equivalent rule? | Development | • Given the OneScore model is active, When post-scoring rules are executed, Then Rule 19 (No Commercial Data) should not be triggered or evaluated. • Given Rule 19 is removed, When credit decisions are processed, Then the system should not reference or apply No Commercial Data logic.
US-016 | As a Business Analyst, I want Ascendion to conduct mandatory test case review and provide BA signoff so that all test scenarios are validated before UAT. | This is an enterprise mandate story covering the requirement for Ascendion to review all test cases and provide Business Analyst signoff before User Acceptance Testing begins. Reference: Enterprise governance requirements. Dependency: All development stories (US-004 through US-015) must be completed. | Governance | • Given all development work is completed, When Ascendion reviews the test cases, Then all test scenarios should be documented and validated. • Given test case review is complete, When the Business Analyst provides signoff, Then the approval should be documented and UAT can proceed.
US-017 | As a Project Manager, I want to receive advance notification for planned configuration changes from the Equifax admin so that Western EF can prepare for changes and minimize disruption. | This is an enterprise mandate story covering the requirement for Equifax to provide advance notification of any planned configuration changes. Reference: Enterprise governance requirements and BRD Timeline section (Slide 10). | Governance | • Given a configuration change is planned by Equifax, When the change is scheduled, Then Western EF should receive advance notification with details of the change. • Given advance notification is provided, When the notification is received, Then it should include the change description, timeline, and potential impact.
US-018 | As a Development Lead, I want to receive final code review support for coding signoff from the Equifax team so that all code meets quality standards before deployment. | This is an enterprise mandate story covering the requirement for Equifax team to provide final code review and coding signoff. Reference: Enterprise governance requirements. | Governance | • Given all development work is completed, When the code is ready for review, Then the Equifax team should conduct a final code review. • Given the code review is complete, When the Equifax team provides signoff, Then the approval should be documented and deployment preparation can proceed.
US-019 | As a QA Analyst, I want the Equifax team to provide production-like test data covering all scenarios so that comprehensive testing can be performed in the sandbox environment. | This is an enterprise mandate story covering the requirement for Equifax to provide comprehensive test data. Reference: BRD Dependencies section (Slide 11) - 'Client will create test data in sandbox' and enterprise governance requirements. Clarification needed: Who is responsible for creating test data - Client or Equifax? The BRD states 'Client will create test data' but enterprise mandate requires Equifax to provide it. | Governance | • Given the sandbox environment is ready for testing, When test data is required, Then Equifax should provide production-like test data covering all business scenarios. • Given test data is provided, When testing is conducted, Then the data should include coverage for all new rules, scores, and edge cases.
US-020 | As a Release Manager, I want to execute deployment validation and post-deployment checks so that the OneScore migration is successfully deployed to production without issues. | This is the deployment story covering release readiness, deployment validation, and post-deployment verification. This includes packaging approved changes for deployment to Sandbox and Production environments, and providing BusinessConnect standard documentation. Reference: BRD Next Steps section (Slide 13) and Timeline (Slide 10). Target Production Release: June 15, 2026. Dependency: All development stories (US-004 through US-015) and governance stories (US-016 through US-019) must be completed. | Deployment | • Given all development and governance stories are completed, When the deployment package is prepared, Then it should include all configuration changes, code changes, and documentation. • Given the deployment is executed in production, When post-deployment checks are performed, Then all OneScore functionality should work as expected and CIDS should be fully removed. • Given the production deployment is complete, When BusinessConnect standard documentation is provided, Then it should include all configuration details and build components. • Given the deployment is validated, When the one-hour admin and train-the-trainer session is conducted, Then Western EF users should be trained on the new OneScore functionality.