## Sheet1
User Story No. | User Story | Description | Phase | Acceptance Criteria
US-001 | As a system administrator, I want to modify Data Provider Products in BusinessConnect to add Equifax OneScore and remove CIDS so that the system uses the updated credit scoring model | Modify Data Provider Products configuration in BusinessConnect: Add Equifax OneScore (SCR2038) and Remove Equifax Commercial Insight Delinquency Score (CIDS) (SCR0117). Dependencies: This configuration must be completed before any Salesforce changes. Assumption: Equifax OneScore field name is confirmed as SCR2038 in BusinessConnect. | Configuration | • Given BusinessConnect Data Provider Products configuration is accessible, When the administrator adds Equifax OneScore (SCR2038) and removes CIDS (SCR0117), Then the system should successfully update the Data Provider Products list with OneScore available and CIDS removed
US-002 | As a system administrator, I want to create new fields for OneScore, ScoreCard Type, and Fraud Victim Alert Indicator so that credit scoring data can be captured and displayed | Create new fields: OneScore on Account, Decision, and Equifax Commercial objects; ScoreCard Type on Account, Decision, and Equifax Commercial objects; Fraud Victim Alert Indicator on Consumer Report object with Data Provider mapping and value fetch; Fraud Victim Alert and Active Duty Alert on Decision object. Dependencies: Field creation must be completed before Apex class modifications. Assumptions: All new fields will follow existing naming conventions; Fraud Victim Alert and Active Duty Alert fields already exist in Consumer Report object. | Configuration | • Given the Salesforce schema is accessible, When the administrator creates OneScore field on Account, Decision, and Equifax Commercial objects, Then the field should be available for data storage and retrieval • Given the Salesforce schema is accessible, When the administrator creates ScoreCard Type field on Account, Decision, and Equifax Commercial objects, Then the field should be available for scorecard classification • Given the Salesforce schema is accessible, When the administrator creates Fraud Victim Alert Indicator field on Consumer Report object with Data Provider mapping, Then the field should successfully fetch and store fraud alert data from the provider • Given the Salesforce schema is accessible, When the administrator creates Fraud Victim Alert and Active Duty Alert fields on Decision object, Then the fields should be available for decision processing
US-003 | As a credit analyst, I want to view Equifax OneScore on Opportunity, Account, Equifax Commercial Report, and Decision pages so that I can access credit scoring information during decision-making | Add Equifax OneScore field to Salesforce UI Pages: Opportunity page, Account page (Relationship section), Equifax Commercial Report page (Credit Information section), and Decision page (Scorecard section). Dependencies: UI changes depend on field creation completion (US-002). Assumption: Existing UI layouts can accommodate the new field without major redesign. | Configuration | • Given OneScore field exists and is populated, When a user views the Opportunity page, Then the OneScore should be displayed in the appropriate section • Given OneScore field exists and is populated, When a user views the Account page Relationship section, Then the OneScore should be displayed • Given OneScore field exists and is populated, When a user views the Equifax Commercial Report Credit Information section, Then the OneScore should be displayed • Given OneScore field exists and is populated, When a user views the Decision Scorecard section, Then the OneScore should be displayed
US-004 | As a system, I want to update the Decision Scorecard to use OneScore as the primary component with Risk Rating and Primary Decision calculation so that credit decisions are based on the new scoring model | Replace existing Commercial Scorecard with new Scorecard logic using OneScore as primary component, including Risk Rating and Primary Decision calculation. Dependencies: Decision Scorecard update depends on OneScore field availability (US-002). Assumption: Existing Scorecard logic will be fully replaced (not merged). | Configuration | • Given the Decision Scorecard configuration is accessible and OneScore field is available, When the system processes a credit decision, Then the Scorecard should use OneScore as the primary component with Risk Rating and Primary Decision calculation applied
US-005 | As a system, I want to implement PG Fraud Alert pre-score rule so that applications with fraud victim alerts are flagged for manual review | Implement Pre-Score Rule 4 (PG Fraud Alert): When any Personal Guarantor (PG) has Fraud Victim Alert from Consumer Report, set Secondary Decision to 'Manual Review'. Implementation: Update OppConsumerController Apex class. Dependencies: Pre-Score rules must be deployed before Post-Score rules; Field US-002 must be completed. Assumption: Fraud Victim Alert field already exists in Consumer Report object. Referenced field from US-002: Fraud Victim Alert on Decision object. | Development | • Given a Consumer Report is processed and any PG has Fraud Victim Alert indicator set to true, When the pre-score rule executes in OppConsumerController, Then the Secondary Decision should be set to 'Manual Review'
US-006 | As a system, I want to implement PG Active Duty Alert pre-score rule so that applications with active duty alerts are flagged for manual review | Implement Pre-Score Rule 5 (PG Active Duty Alert): When any Personal Guarantor (PG) has Active Duty Alert from Consumer Report, set Secondary Decision to 'Manual Review'. Implementation: Update OppConsumerController Apex class. Dependencies: Pre-Score rules must be deployed before Post-Score rules; Field US-002 must be completed. Assumption: Active Duty Alert field already exists in Consumer Report object. Referenced field from US-002: Active Duty Alert on Decision object. | Development | • Given a Consumer Report is processed and any PG has Active Duty Alert indicator set to true, When the pre-score rule executes in OppConsumerController, Then the Secondary Decision should be set to 'Manual Review'
US-007 | As a system, I want to implement Exceeds App Only Limit post-score rule so that high-exposure approved applications are flagged for manual review | Implement Post-Score Rule 11 (Exceeds App Only Limit): When Primary Decision is 'Approve' and Aggregate Exposure exceeds $500K, set Post-Score Action to 'Manual Review' and update Secondary Decision including Primary Decision. Implementation: Move logic from OppConsumerController to PaynetReportBatch. Dependencies: Pre-Score rules must be deployed before Post-Score rules; Field US-002 must be completed. Clarifying Questions: 1) What is the exact definition and calculation method for Aggregate Exposure? 2) Should the $500K threshold be configurable via Custom Label? 3) What should happen if Aggregate Exposure data is unavailable? | Development | • Given a credit decision is processed with Primary Decision as 'Approve' and Aggregate Exposure is greater than $500K, When the post-score rule executes in PaynetReportBatch, Then the Post-Score Action should be set to 'Manual Review' and Secondary Decision should be updated to include the Primary Decision
US-008 | As a system, I want to implement Exceeds Comparable Credit post-score rule so that applications with insufficient credit history are flagged for manual review | Implement Post-Score Rule 22 (Exceeds Comparable Credit): When Total Finance Amount exceeds $350K, Primary Decision is 'Approve', and Single Highest Credit is less than 50% of Equipment Cost, set Post-Score Action to 'Manual Review' and update Secondary Decision. Implementation: Add new logic in PaynetReportBatch using Custom Label for Total Finance Amount threshold. Field Mapping: Total Finance Amount → Opportunity.Total_Finance_Amount__c, Single High Credit → Equifax Commercial.TotalCreditLimit, Equipment Cost → Opportunity.Equipment_Cost__c. Calculation: (Single High Credit / Equipment Cost) %. Dependencies: Field US-002 must be completed. Assumptions: Total Finance Amount field already exists on Opportunity object; Custom Labels will be used for configurable thresholds. Clarifying Questions: 1) Should the $350K threshold be configurable? 2) How should the system handle null or zero values in Equipment Cost? 3) Should there be a minimum Equipment Cost threshold to avoid division errors? | Development | • Given a credit decision is processed with Total Finance Amount greater than $350K and Primary Decision as 'Approve' and Single Highest Credit is less than 50% of Equipment Cost, When the post-score rule executes in PaynetReportBatch, Then the Post-Score Action should be set to 'Manual Review' and Secondary Decision should be updated accordingly
US-009 | As a system, I want to implement OneScore Consumer Only post-score rule so that approved applications with consumer-only scorecards are flagged for manual review | Implement Post-Score Rule 23 (OneScore Consumer Only): When Primary Decision is 'Approve' and Scorecard is Consumer-only (no commercial data), apply Manual Review logic. Implementation: Add logic in PaynetReportBatch. Dependencies: Field US-002 must be completed; Decision Scorecard update (US-004) must be completed. Clarifying Questions: 1) What specific field or indicator determines if a Scorecard is 'Consumer-only'? 2) Should this rule apply to all consumer-only scenarios or only specific score ranges? 3) Are there any exceptions where consumer-only approvals should not trigger manual review? | Development | • Given a credit decision is processed with Primary Decision as 'Approve' and the Scorecard is identified as Consumer-only with no commercial data, When the post-score rule executes in PaynetReportBatch, Then the Manual Review logic should be applied
US-010 | As a system, I want to comment out all CIDS-related code references so that the decommissioned scoring model is cleanly removed from the codebase | CML Migration (CIDS Decommission - Code Cleanup): Comment out all references to CIDS-related fields across codebase in CommercialReportBatch (CIDS_Score__c mapping to Decision), PaynetReportBatch (CIDS_Score__c in query, WEF_Score_Tier__c mapping, CIDS_Score_Points__c in query), OppConsumerController (WEF_Score_Tier__c usage and null assignment), and CommercialReportBatch (CIDS_Score_Points__c mapping). Related Flow (Decision WEF Score Tier) is not implemented. Dependencies: CML migration must be completed in a separate release to avoid conflicts. Assumption: Commented code will remain in codebase for audit purposes. Clarifying Questions: 1) Should commented code be removed entirely after a retention period? 2) Are there any downstream systems or reports that still reference CIDS fields? 3) Should there be a rollback plan if OneScore integration fails? | Development | • Given the codebase contains CIDS-related field references in CommercialReportBatch, PaynetReportBatch, and OppConsumerController, When the code cleanup is performed, Then all CIDS_Score__c, WEF_Score_Tier__c, and CIDS_Score_Points__c references should be commented out and the code should compile successfully without errors
US-011 | As a system administrator, I want to create checkbox fields on Decision object for tracking rule execution so that I can monitor which business rules were triggered for each decision | Create Viewed Variables (Tracking Rule Execution): Create Checkbox Fields on Decision Object for PG Fraud Alert, PG Active Duty Alert, OneScore Consumer Only, and Exceeds Comparable Limit. Logic: Set checkbox to TRUE when respective rule executes. Dependencies: Field creation must be completed before rule implementation (US-005 through US-009). Assumption: Viewed Variables will be used for internal tracking only (not exposed in UI). Clarifying Questions: 1) Should these tracking fields be visible in any UI or reports? 2) Should there be a mechanism to reset these flags? 3) Are there any audit or compliance requirements for tracking rule execution history? | Configuration | • Given the Decision object schema is accessible, When the administrator creates checkbox fields for PG Fraud Alert, PG Active Duty Alert, OneScore Consumer Only, and Exceeds Comparable Limit, Then the fields should be available for tracking rule execution • Given a business rule executes for a decision, When the respective rule completes processing, Then the corresponding checkbox field should be set to TRUE
US-012 | As a Quality Assurance team, I want mandatory test case review and BA signoff from Ascendion so that all user stories meet quality standards before deployment | Enterprise Mandate: Ascendion must perform mandatory test case review and provide Business Analyst signoff for all user stories before deployment. This ensures quality standards, requirement alignment, and acceptance criteria validation. | Governance | • Given all test cases are documented for the user stories, When Ascendion QA team reviews the test cases, Then the BA must provide formal signoff confirming all acceptance criteria are covered and testable
US-013 | As a development team, I want advance notification for planned configuration changes from the Equifax admin so that I can prepare for integration impacts | Enterprise Mandate: Equifax admin must provide advance notification for any planned configuration changes to BusinessConnect or data provider products. This ensures proper coordination, impact assessment, and deployment planning. | Governance | • Given a configuration change is planned in BusinessConnect or data provider products, When the Equifax admin schedules the change, Then advance notification must be sent to the development team with sufficient lead time for impact assessment
US-014 | As a development team, I want final code review support and coding signoff from the Equifax team so that integration logic meets technical standards | Enterprise Mandate: Equifax team must provide final code review support and coding signoff for all integration logic, API implementations, and data provider mappings. This ensures technical accuracy, security compliance, and integration best practices. | Governance | • Given all code changes are completed for BusinessConnect integration, When the development team requests code review, Then the Equifax team must review and provide formal coding signoff confirming technical standards are met
US-015 | As a testing team, I want provision of production-like test data covering all scenarios from the Equifax team so that I can validate all business rules and edge cases | Enterprise Mandate: Equifax team must provide production-like test data covering all scenarios including fraud alerts, active duty alerts, various score ranges, consumer-only scorecards, and edge cases. This ensures comprehensive testing and validation of all business rules. | Governance | • Given test data requirements are defined for all user stories and business rules, When the testing team requests test data from Equifax, Then production-like test data must be provided covering all scenarios including fraud alerts, active duty alerts, score variations, consumer-only cases, and edge cases
US-016 | As a release manager, I want to validate release readiness and perform deployment validation with post-deployment checks so that the Equifax OneScore integration is successfully deployed to production | Deployment User Story: Covers release readiness validation, deployment execution, and post-deployment verification for Equifax OneScore integration. Includes validation of all configuration changes (US-001 through US-004), development changes (US-005 through US-010), and tracking fields (US-011). Dependencies: All configuration, development, and governance stories must be completed. Deployment sequence: 1) Equifax OneScore configuration in BusinessConnect, 2) Field creation in Salesforce, 3) Pre-Score rules deployment, 4) Post-Score rules deployment, 5) CML migration in separate release, 6) UI changes, 7) Decision Scorecard update. Clarifying Questions: 1) What is the rollback plan if deployment fails? 2) Are there any maintenance windows or blackout periods? 3) What are the success criteria for post-deployment validation? | Deployment | • Given all user stories are completed and tested, When the release manager validates release readiness, Then all configuration changes, development changes, and governance requirements must be confirmed complete • Given the deployment package is prepared, When the deployment is executed to production, Then all components should deploy successfully without errors following the defined deployment sequence • Given the deployment is completed, When post-deployment checks are performed, Then all fields should be accessible, all rules should execute correctly, OneScore should display on UI pages, and the Decision Scorecard should use the new logic